## Slide 1: AI CHATBOT
For
Sales & Customer Support
By : Winston Sanjith

## Slide 2: INDEX
Project Scope
Flow Diagram
Business Requirements Document (BRD)
Work Breakdown Structure (WBS)
User Stories
Additional Features

## Slide 3: PROJECT SCOPE
AI-powered chatbot integrated into the company’s website or application.
Processed and embedded knowledge base using OpenAI’s embedding model (emails, manuals, FAQs).
Vector database setup to enable retrieval-augmented responses.
Web-based chat interface (for sales reps and customers).
Feedback and escalation system (to route unresolved queries to human agents).
Admin dashboard for uploading documents, monitoring interactions, and chatbot performance.
In-Scope (Deliverables)

## Slide 4: PROJECT SCOPE
Voice-based AI assistant or phone/IVR integration.
Integration with CRM systems (Salesforce, Zoho, etc.) in the current phase.
Multilingual support (to be considered as additional feature).
Out of-Scope (Exclusions)

## Slide 5: PROJECT SCOPE
Reduce average query response time for both sales teams and customers.
1
Reduce dependency on technical engineers by enabling 24/7 intelligent query resolution.
2
Automate responses to solve user queries faster and reduce site traffic.
3
Automate responses to repetitive technical questions.
4
Improve customer satisfaction scores post-implementation.
5
Objectives

## Slide 6: PROJECT SCOPE
Budget: Licenses, Databases, including Cloud usage, OpenAI API, Hosting and Development costs must adhere to client budget.
Timeline: Must be delivered within the expected timeline.
Technology: Restricted to OpenAI’s GPT-4o and available embedding models.
Scope: Initial chatbot limited to English text queries and document-based answers only.
Data: Accuracy depends on the quality of provided documentation and email threads.
Constraints

## Slide 7: FLOW DIAGRAM
AI Chatbot pops up to help
Start
User clicks
Yes/No
End
Process User Query
No
Generate Embedding
Checks for match/relevant files in Database
Match found
Yes/No
Collect Feedback
Escalate query to Technical Engineer
No
Retrieve relevant documents
Construct Prompt with user query and documents
Generate response using GPT-4o
Return response to user
Yes
Yes

## Slide 8: BUSINESS REQUIREMENT DOCUMENT-BRD
Executive Summary
The AI Chatbot project seeks to implement an intelligent, OpenAI powered chatbot that provides instant technical support to sales teams and customers. The system is designed to reduce dependency on technical engineers, improve customer response time, and create a scalable support platform. This document outlines the key elements required to implement the chatbot system.

## Slide 9: BUSINESS REQUIREMENT DOCUMENT-BRD
Project Objectives
Specific: Develop and deploy an AI chatbot accessible via the company’s website or internal portal.
Measurable: Achieve at least 80% accuracy in resolving common technical queries.
Achievable: Use OpenAI GPT-4o API, curated internal documents, and vector database to deliver the solution.
Relevant: Improve operational efficiency and customer satisfaction.
Time-bound: Complete the project and go live within 12 weeks.

## Slide 10: BUSINESS REQUIREMENT DOCUMENT-BRD
Needs Statement
Currently, sales teams and customers face long delays in receiving answers to technical questions, as these depend on busy engineers. This results in reduced productivity, lost business opportunities, and poor customer experience. An AI chatbot will automate responses to common queries using existing documentation, making the process faster and more reliable.

## Slide 11: BUSINESS REQUIREMENT DOCUMENT-BRD
Project Scope
In Scope:
Chatbot frontend for customer and sales interactions
Integration with OpenAI GPT-4o for natural language understanding
Document processing pipeline and vector database
Feedback and escalation workflows
Admin dashboard for content management and analytics
Out of Scope:
Voice interaction capabilities
CRM/ERP integrations
Multilingual support (planned for future)

## Slide 12: BUSINESS REQUIREMENT DOCUMENT-BRD
Requirements
Functional Requirements:
Accept user queries via chat interface
Retrieve and rank relevant document chunks
Generate responses using GPT-4o
Escalate low-confidence queries to human agents
Allow users to rate responses
Enable admin to upload/update content and view logs
Technical Requirements:
Use OpenAI API (GPT-4o, Embedding)
Store vectorized documents in a searchable database (FAISS or Pinecone)
Host system on scalable infrastructure with secure access

## Slide 13: BUSINESS REQUIREMENT DOCUMENT-BRD
Project Constraints
Must adhere to client's budget.
Project must be completed within the given timeframe (approx:12 weeks)
Technology limitations (GPT-4o)
Quality depends on completeness and accuracy of training documents

## Slide 14: BUSINESS REQUIREMENT DOCUMENT-BRD
SWOT Analysis
Strengths | Weaknesses
Reduces Engineer Workload | Dependent on document quality
Enhances Response Time | Requires regular content updates
Uses Advance AI | Limited technical resources
Opportunities | Threats
Future multilingual voice support | OpenAI API prices and limits
Integration with CRM for full pipeline | Incorrect AI responses without supervision

## Slide 15: BUSINESS REQUIREMENT DOCUMENT-BRD
Stakeholders
Sponsor: Chief Technology Officer (CTO)
Business Owner: Sales Director
Project Manager: Appointed internal lead
End Users: Sales Team, Customers
Technical Team: Backend, Frontend, DevOps
Support Team: Customer Support, SMEs

## Slide 16: BUSINESS REQUIREMENT DOCUMENT-BRD
Schedule and Timeline
MILESTONE | TIMEFRAME(approx)
Requirements Finalization | Week 1
Document Curation and Embedding | Week 2-3
Vector DB and GPT Integration | Week 4-5
Chatbot Frontend Development | Week 6-7
Feedback and Escalation Logic | Week 8
Admin Panel Implementation | Week 9
Internal Testing(UAT) | Week 10
Deployment | Week 11-12

## Slide 17: BUSINESS REQUIREMENT DOCUMENT-BRD
Financial Statement (Estimated)
ITEM | ESTIMATED COST (INR)
Developer Resources | 5,00,000
OpenAI API Usage | 25,000
Hosting and Infrastructure | 25,000
Project Management | 2,00,000
Contingency Buffer | 30,000
Total | 7,80,000

## Slide 18: BUSINESS REQUIREMENT DOCUMENT-BRD
Cost-Benefit Analysis
Estimated Savings: ₹90,000/month by reducing support engineer dependency
Customer Retention Impact: Expected 20% increase due to faster support
Sales Efficiency Gain: Faster deal closures with instant query resolution
ROI Timeline: Expected within 8-10 months post-deployment

## Slide 19: BUSINESS REQUIREMENT DOCUMENT-BRD
Functional Specifications
User Roles & Permissions
Customer/Sales Rep: Submit queries, give feedback
Admin: Upload docs, view logs, manage escalations
Functional Modules
Chat UI for user queries and feedback
Document retrieval using embeddings and vector DB
GPT-4o response generation
Admin dashboard with file upload and analytics
System Architecture
User → Vector Search → Prompt to GPT-4o → Response → Feedback log

## Slide 20: BUSINESS REQUIREMENT DOCUMENT-BRD
Functional Specifications
API Integrations
GPT-4o and Embedding APIs
Document retrieval via FAISS/Pinecone
Error Handling
Timeout/Error → Fallback message
No match → Escalation to support
UI Requirements
Responsive, branded chatbot interface
Admin dashboard with document viewer and stats

## Slide 21: BUSINESS REQUIREMENT DOCUMENT-BRD
Glossary
GPT-4o: OpenAI's generative model
Embedding: Numerical vector representation of text used for semantic search
RAG (Retrieval-Augmented Generation): A method combining document retrieval and generative AI
Vector Database: Specialized DB that supports similarity search of vector embeddings
UAT: User Acceptance Testing
SME: Subject Matter Expert
Chatbot: Conversational agent responding to text queries

## Slide 22: WORK BREAKDOWN STRUCTURE-WBS
Requirement Gathering​
Stakeholder Identification
​
Document Curation and Cleaning
​
Tool & Technology Selection
Backend Design-RAG Architecture
Vector Database Setup-FAISS or Pinecone
API Flow Design-GPT4o & Embeddings
Chat UI Design (Customer & Sales)
Input Handling & Display Logic
Feedback & Rating UI
Error Message & Escalation UI
Preprocess & Embedding Pipeline
Document Retrieval Engine
GPT-4o Integration Logic
Confidence Scoring & Escalation Logic
Secure Login Page​
Upload/Manage Knowledge Files
View Chat Logs & Escalations
​
View Usage Analytics
Connect Frontend & Backend
Hosting on AWS/GCP/Local Server
API Key & Authentication Config
Logging & Monitoring Setup
Unit Testing (Frontend & Backend)
Integration Testing
UAT with Sales Team
Load Testing & Performance Tuning
Final Deployment
Stakeholder Demo
Post-Launch Monitoring
Feedback Collection & Hotfixes
Timeline & Milestone Tracking
Risk & Change Management
Status Reporting
Documentation & Handover
Project Planning
Frontend Development
Backend Development
Admin Dashboard
Integration and Hosting
Testing and QA
Deployment and Launch
Project Management
System Design and Architecture
MILESTONE
Week 1
Week 2-3
Week 4-5
Week 6-7
Week 8
Week 9
Week 10
Week 11-12

## Slide 23: USER STORIES
User Story 1: Customer Query Resolution
As a customer,
I want to ask product-related technical questions via the chatbot on the
website, so that I can get instant and reliable answers without waiting for a
human agent.
Acceptance Criteria:
  Chatbot should allow free-text input.
  Response should be generated within 5 seconds.
  If confidence is low, chatbot should escalate to human.

## Slide 24: USER STORIES
User Story 2: Sales Team Support
As a sales executive,
I want to use the chatbot to clarify technical specs during a live sales
call, so that I can close deals faster without depending on a technical
engineer.
Acceptance Criteria:
  System must be accessible from desktop/mobile.
  Chat logs should be saved for reference.
  AI should cite the document used for the answer.

## Slide 25: USER STORIES
User Story 3: Admin Document Upload
As a admin,
I want to upload and manage technical documents through a
dashboard, so that the chatbot always has access to the most up-
to-date knowledge.
Acceptance Criteria:
  Admin can log in securely.
  Supported formats: PDF, DOCX, TXT.
  Uploaded documents should trigger re-indexing automatically.

## Slide 26: USER STORIES
User Story 4: Feedback Collection
As a customer,
I want to rate the chatbot’s response after each interaction, so that the
system can improve its accuracy and support quality over time.
Acceptance Criteria:
  User can give thumbs up/down or 5-star rating.
  Feedback is saved to the backend for analytics.
  Optionally allow users to provide written feedback.

## Slide 27: USER STORIES
User Story 5: Escalation to Human Agent
As a customer,
I want to be automatically connected to a human if the chatbot
can’t answer my query, so that I don’t get stuck with incorrect or
incomplete information.
Acceptance Criteria:
  Bot must evaluate confidence score in response.
  If below threshold, escalate and notify technical support.
  Conversation should be handed off with context/history.

## Slide 28: ADDITIONAL FEATURE - 1
User Story : Personalized Chat History
As a returning customer, I want to view my previous chatbot interactions, so that I can refer back to earlier responses and
follow up without repeating myself.
Acceptance Criteria:
The chatbot should recognize returning users (via session/cookie or login).
Previous queries and answers should be visible in a 'Chat History' section.
Follow-up questions can be linked to previous conversations.
Users can delete their chat history if desired (for privacy compliance).
Each entry in the history should be timestamped and searchable.
Why It Adds Value:
Reduces frustration for repeat users
Makes the chatbot feel more intelligent and human-like
Helps track complex queries over time
Useful for internal sales reps dealing with long-term deals

## Slide 29: ADDITIONAL FEATURE - 2
User Story : Regional Language
As a regional customer, I want to interact with the chatbot in my native language (e.g. Tamil, Telugu), so that I can better
understand the product and receive support in a language I’m comfortable with.
Acceptance Criteria:
User should be prompted to select a preferred language at the start or via chatbot settings based on location of device.
Chatbot should support translation of both user input and bot response.
Initial languages supported: Tamil, Telugu, Kannada, Malayalam and Hindi (more in future).
Admin dashboard should support uploading translated documents for context.
Why It Adds Value:
Expands accessibility across diverse regions in India
Improves satisfaction and trust among non-English-speaking users
Gives the company a competitive edge in regional markets
Reduces language barriers for product support and onboarding

## Slide 30
END
Business Analyst – Winston Sanjith